## Slide 1
PHASE 1 - NIGHTTIME
WORK ACTIVITIES
A11 Newmarket Rd (Eastbound)
Site Clearance
Earthworks
Drainage (excluding tanks)
Ducting for traffic signals
Kerbs
Carriageway Widening
Newmarket Road
Widening
N.T.S
C.D.C
S.L
09-04-2024
Newmarket Road
Widening
Phase 1
Nearside Lane Closure
Safety barrier installed
Outside lane of
roundabout closed
KEY
Works Area
Traffic Flow
Safety Zone
05513-CC-P1
Nearside Lane Closure
Safety barrier installed
A11 Newmarket Rd (Westbound)
Site Clearance
Earthworks
Drainage (excluding tanks)
Kerbs
Carriageway Widening
Eastbound Lane Overnight Closure
28/04 – 07/07
10 weeks
W/B overnight lane closure
28/04 – 29/05
4.4 weeks

## Slide 2
PHASE 1 - DAYTIME
WORK ACTIVITIES
A11 Newmarket Rd (Eastbound)
Drainage (Aqua Cell Tank North)
A11 Newmarket Rd (Roundabout)
Drainage (Aqua Cell Tank)
Ducting for traffic signals
Grasscrete
Newmarket Road
Widening
N.T.S
C.D.C
S.L
09-04-2024
Newmarket Road
Widening
Phase 1
Outside lane of
roundabout closed
Aquacell Tank
To be installed
Aquacell Tank
To be installed
KEY
Works Area
Traffic Flow
Safety Zone
05513-CC-P1
Outside lane of
roundabout closed
24/7 Lane closures on Rbt
5 weeks 17/03 to 22/04

## Slide 3
PHASE 2 - DAYTIME
WORK ACTIVITIES
Roundhouse Way Roundabout (North Arm)
Break out northern splitter island &
install temp carriageway widening
Drainage
Kerb re-alignment
Ducting for traffic signals
Carriageway Widening
Newmarket Road
Widening
N.T.S
C.D.C
09-04-2024
Newmarket Road
Widening
Phase 2
S.L
KEY
Works Area
Traffic Flow
Safety Zone
05513-CC-P2
Splitter Island Closed.
Footpath diversion route
Splitter Island Closed.
24/7 lane closures on Rbt
24/04 – 29/05
Also 1 week, night-time, one-way closure on Roundhouse Way to remove splitter island

## Slide 4
PHASE 3 - DAYTIME
WORK ACTIVITIES
Roundhouse Way Roundabout (North Arm)
Site Clearance
Earthworks
Drainage
Ducting for traffic signals
Kerbs
Carriageway reconfiguration
Newmarket Road
Widening
N.T.S
C.D.C
09-04-2024
Newmarket Road
Widening
Phase 3
S.L
KEY
Works Area
Traffic Flow
Safety Zone
05513-CC-P3
Bus stop temporarily closed &
Relocated to enable carriageway re-alignment
Temporary splitter island
Splitter Island Closed.
24/7 lane closures to Rbt.
3.6 weeks 30/05 – 25/06

## Slide 5
PHASE 4 - DAYTIME
WORK ACTIVITIES
Newmarket Road
Widening
N.T.S
C.D.C
09-04-2024
Newmarket Road
Widening
Phase 4
Roundhouse Way Roundabout
(Splitter island North)
Drainage
Ducting for traffic signals
Kerbs
Splitter Island reconfiguration
KEY
Works Area
Traffic Flow
Safety Zone
05513-CC-P4
S.L
Splitter Island Closed.
Footpath diversion route
Splitter Island Closed.
24/7 lane closures to Rbt
2.4 weeks 26/06 to 15/07

## Slide 6
PHASE 5 – NIGHT TIME ROAD CLOSURE
WORK ACTIVITIES
Roundabout
Plane out\surface course
Road markings
Install Street lighting (By client)
Install traffic signals (by Client)
Signage
Splitter Island (West)
Kerbs
Splitter Island reconfiguration
Change streetlight lanterns (By Client)
Traffic Signals (By Client()
Newmarket Road
Widening
N.T.S
C.D.C
09-04-2024
Newmarket Road
Widening
Phase 5
KEY
Works Area
Traffic Flow
Safety Zone
05513-CC-P5
S.L
Overnight closures
2.0 weeks 14/07 – 04/08

## Slide 7
PHASE 5 – NIGHTTIME ROAD CLOSURE
POTENTIAL HGV DIVERSION ROUTE
15 MINUTES\9.1 MILES

## Slide 8
PHASE 5 – NIGHTTIME ROAD CLOSURE
POTENTIAL DIVERSION ROUTE A11 NEWMARKET (SOUTH)
14 MINUTES\6.5 MILES

## Slide 9
PHASE 5 – NIGHTTIME ROAD CLOSURE
POTENTIAL DIVERSION ROUTE A11 NEWMARKET (NORTH)
8 MINUTES\4.7 MILES